## 📋 Overview
HEALCONNECT — Project Execution Plan
Professional Wellness Marketplace • MVP Target: 45 Days • Infrastructure: Microsoft Azure
PHASE SUMMARY
Phase | Duration | Period | Goal | Key Owner | Tasks | Status | Risk
Phase 1 — MVP | 45 Days | D1 – D45 | Chat+Audio marketplace launch | All Teams | 45 | 🔴 Critical | High
Phase 2 — Growth | 45 Days | D46 – D90 | Engagement & self-service tools | Backend + Mobile | 28 | 🟡 Planned | Medium
Phase 3 — Scale | 70 Days | D91 – D160 | Physical marketplace, Video, AI, Intl. | All Teams | 24 | ⬜ Backlog | Medium
LEGEND — TASK TYPE
| Frontend |  | User-facing UI work (React Native / Next.js)
| Backend |  | API, DB, business logic (Node.js / PostgreSQL)
| DevOps |  | Infrastructure, CI/CD, Azure provisioning
| Assets |  | UI/UX design, documentation, cost analysis
| QA |  | Testing, validation, performance benchmarks
LEGEND — PRIORITY
| Critical |  | Blocks launch — must complete before any handoff
| High |  | Important for sprint goal — prioritise in daily standup
| Medium |  | Complete within sprint window
| Low |  | Nice-to-have; defer if blocked
TEAM ROSTER
Name | Role | Domain | Key Responsibilities
Rahul | Frontend Lead | Frontend | Landing page, Hero, Auth UI, Dashboard
Deepak | Frontend Dev | Frontend | Feature highlights, Pricing, Library UI
TBD | Backend Lead | Backend | Auth, APIs, Payments, Real-time chat
TBD | DevOps / Infra | DevOps | Azure setup, Docker, CI/CD, Deployments
TBD | UI/UX Designer | Assets | Figma designs, Design system, Mockups
TBD | QA Engineer | QA | Test plans, E2E testing, Performance

## 🚀 Phase 1 — MVP (45 Days)
HealConnect — Phase 1 — 45-Day Aggressive MVP ¦ Chat + Audio Marketplace Launch ¦ Sprint 1–6B ¦ D1–D45
Phase 1 — 45-Day Aggressive MVP ¦ Chat + Audio Marketplace Launch ¦ Sprint 1–6B ¦ D1–D45
# | TASK NAME | DESCRIPTION | TASK TYPE | PRIORITY | STATUS | ASSIGNED TO | SPRINT / WEEK | DUE DATE | DEPENDENCIES | NOTES / RELATED DOCS
▸ SPRINT 1 (D1–D7) — UI/UX Design Lock + Azure Infrastructure Setup
1 | Design System & Figma Setup | Establish design tokens (colours, typography, spacing, iconography). Set up shared Figma workspace and component library. | Assets | Critical | Not Started | UI/UX Designer | Sprint 1 (D1–D7) | 28 Apr 2025 | — | Scope §5 — Must lock within 5-7 days. No redesigns after Day 7.
2 | Landing Page – Hero Section (Figma → Approve → Code) | Design hero section with headline, CTA, practitioner imagery, and trust signals. Pass to dev after approval. | Frontend | Critical | Not Started | Rahul | Sprint 1 (D1–D7) | 28 Apr 2025 | Design System locked | Designs → Approve → Code workflow. Rahul owns dev.
3 | Landing Page – Feature Highlights Section | Design & code feature cards: Chat, Audio Call, Verified Experts, Wallet, Free Tools. | Frontend | High | Not Started | Deepak | Sprint 1 (D1–D7) | 28 Apr 2025 | Design System locked | Deepak owns dev.
4 | Landing Page – Pricing Section | Per-minute pricing display for practitioner categories. Wallet recharge CTA. Responsive layout. | Frontend | High | Not Started | TBD | Sprint 1 (D1–D7) | 28 Apr 2025 | Design System locked | Designs → Approve → Code
5 | Landing Page – Login / Sign-In Section | OTP-based login, Google Sign-In button, Apple Sign-In button. Responsive auth entry point. | Frontend | Critical | Not Started | TBD | Sprint 1 (D1–D7) | 28 Apr 2025 | Design System locked | Designs → Approve → Code
6 | Azure Infrastructure Provisioning | Provision: App Service (Node.js), Azure DB for PostgreSQL Flexible Server, Redis Cache, Blob Storage, API Management, Notification Hubs. Configure VNet, NSGs, and Key Vault. | DevOps | Critical | Not Started | DevOps Eng. | Sprint 1 (D1–D7) | 28 Apr 2025 | — | Scope §7.4 — India Central region. Must run parallel to design.
7 | Database Schema Design (The Blueprint) | ER diagram covering: users, practitioners, sessions, messages, wallet_transactions, payouts, ratings, KYC_documents, products. Review with backend team before implementation. | DevOps | Critical | Not Started | Backend Lead | Sprint 1 (D1–D7) | 28 Apr 2025 | Azure PostgreSQL provisioned | Scope §7.2 — Use PostgreSQL Flexible Server. Include indexes.
8 | CI/CD Pipeline Setup (GitHub Actions → Azure) | Create GitHub Actions workflows: build → test → deploy to Azure App Service for dev and prod branches. Environment variables via Azure Key Vault. | DevOps | Critical | Not Started | DevOps Eng. | Sprint 1 (D1–D7) | 28 Apr 2025 | Azure App Service provisioned | Scope §7.4 — GitHub Actions + Azure DevOps Pipelines.
▸ SPRINT 2 (D8–D14) — Authentication, Onboarding & Expert Listing
9 | Backend Security Logic – JWT Auth & Refresh Token Rotation | Implement JWT issuance, verification, and refresh token rotation. Stateless auth with Redis-backed token blacklisting. | Backend | Critical | Not Started | Backend Lead | Sprint 2 (D8–D14) | 5 May 2025 | DB Schema | Scope §9.2 — JWT + refresh rotation. OWASP Top 10.
10 | OTP Authentication via Twilio (Phone Login) | Integrate Twilio SMS for OTP-based phone number registration and login. Rate-limit OTP requests. Expire OTPs after 5 minutes. | Backend | Critical | Not Started | Backend Lead | Sprint 2 (D8–D14) | 5 May 2025 | JWT Auth logic | Scope §5.1, §13 — Twilio for OTP. Consider Azure Comm Services as fallback.
11 | Google Sign-In & Apple Sign-In Integration (Backend) | OAuth 2.0 flows for Google and Apple. Token verification endpoint. Create user record on first login. | Backend | High | Not Started | Backend Lead | Sprint 2 (D8–D14) | 5 May 2025 | JWT Auth logic | Scope §5.1 — Required for App Store compliance (Apple Sign-In mandatory on iOS).
12 | Middleware Protection (Route Guards & Rate Limiting) | Express middleware: auth guard on protected routes, request rate limiting (express-rate-limit + Redis), input sanitisation, CORS config. | Backend | Critical | Not Started | Backend Lead | Sprint 2 (D8–D14) | 5 May 2025 | JWT Auth logic | Scope §9.2 — Rate limiting on all public endpoints.
13 | Email Verification (SendGrid) | Verification email on registration, password-reset email flow. HTML email templates branded for HealConnect. | Backend | High | Not Started | Backend Lead | Sprint 2 (D8–D14) | 5 May 2025 | OTP Auth | Scope §13 — SendGrid for transactional email.
14 | Authentication Integration (Frontend – Login/Register Screens) | Wire login, OTP verification, Google/Apple sign-in flows to backend APIs. Handle error states, loading indicators, and deep-link redirects. | Frontend | Critical | Not Started | Rahul | Sprint 2 (D8–D14) | 5 May 2025 | Backend Auth APIs live | Use mock APIs first, swap to real once backend ready.
15 | User & Practitioner Profile APIs | CRUD endpoints for user profiles (name, DOB, birth place, gender, wellness interests). Practitioner profiles (bio, specialties, certifications, rate, languages). Profile photo upload to Azure Blob. | Backend | High | Not Started | Backend Lead | Sprint 2 (D8–D14) | 5 May 2025 | DB Schema, Azure Blob provisioned | Scope §5.1, §5.9 — Photo upload to Blob Storage.
16 | Expert Discovery & Listing Page (Frontend) | Searchable/filterable practitioner directory. Filters: specialty, language, rating, price/min, availability. Expert profile cards with Online Now indicator. | Frontend | High | Not Started | Deepak | Sprint 2 (D8–D14) | 5 May 2025 | Profile APIs | Scope §5.2 — Use mock data initially.
▸ SPRINT 3 (D15–D21) — Wallet, Payments & Expert Profiles
17 | Wallet System (Backend) – Balance, Credits, Transactions | Wallet entity per user. Recharge, debit, credit operations. Transaction ledger with atomic DB transactions. GST-compliant invoicing logic. | Backend | Critical | Not Started | Backend Lead | Sprint 3 (D15–D21) | 12 May 2025 | DB Schema | Scope §5.4 — Must be atomic to prevent double-spend.
18 | Razorpay Payment Gateway Integration | Razorpay order creation, payment capture webhooks, refund initiation. Support: UPI, cards, net banking, wallets. Test in Razorpay sandbox. | Backend | Critical | Not Started | Backend Lead | Sprint 3 (D15–D21) | 12 May 2025 | Wallet System | Scope §5.4 — Recharge denominations: ₹99/199/499/999/custom. PCI-DSS via Razorpay.
19 | Per-Minute Billing Engine | Session billing timer: debit user wallet every 60 seconds during active session. Grace period (60 sec) before auto-end. Concurrent session safety with Redis locks. | Backend | Critical | Not Started | Backend Lead | Sprint 3 (D15–D21) | 12 May 2025 | Wallet System | Scope §5.3 — Critical for monetisation. Redis-based distributed lock.
20 | Wallet UI (Frontend) – Recharge & Balance Display | Wallet balance in header. Recharge modal with preset amounts (₹99/199/499/999) and custom input. Payment method selection. Transaction history view. | Frontend | High | Not Started | Rahul | Sprint 3 (D15–D21) | 12 May 2025 | Razorpay integration, Wallet API | Scope §5.4 — Balance always visible.
21 | Expert Profile Page (Frontend) – Full Detail View | Expert profile: photo, bio, specialties, certifications, languages, experience, per-min rate, session count, star rating, reviews. Favourite/save button. Book Now CTA. | Frontend | High | Not Started | Deepak | Sprint 3 (D15–D21) | 12 May 2025 | Profile APIs | Scope §5.2 — Verified badge, Online Now indicator.
22 | Azure Blob Storage – Profile Photo & KYC Upload | Multer + Azure Blob SDK for file uploads. Private containers for KYC docs. CDN-backed public container for profile photos. File-type and size validation. | DevOps | High | Not Started | DevOps Eng. | Sprint 3 (D15–D21) | 12 May 2025 | Azure Blob provisioned | Scope §7.4 — KYC in private, photos via Azure CDN.
▸ SPRINT 4 (D22–D28) — Real-Time Chat, Audio Call & Session Flow
23 | Real-Time Chat Infrastructure (Socket.IO + Azure Web PubSub) | Socket.IO server with Azure Web PubSub for horizontal scaling. Chat rooms per session. Message persistence in PostgreSQL. Read receipts and typing indicators. | Backend | Critical | Not Started | Backend Lead | Sprint 4 (D22–D28) | 19 May 2025 | Per-Minute Billing Engine | Scope §7.2 — Socket.IO + Redis Pub/Sub. <200ms message latency.
24 | Agora.io Audio Call Integration | Agora RTC SDK integration for in-app VoIP calls. Token generation server-side. Channel management per session. Call quality feedback hook post-session. | Backend | Critical | Not Started | Backend Lead | Sprint 4 (D22–D28) | 19 May 2025 | Per-Minute Billing Engine | Scope §5.3, §13 — Agora for audio. Video deferred to Phase 3.
25 | Chat UI (Frontend) – Real-Time Session Interface | Chat screen: message bubbles, send input, session timer overlay, wallet balance warning, end session button. Socket.IO client integration. | Frontend | Critical | Not Started | Rahul | Sprint 4 (D22–D28) | 19 May 2025 | Real-Time Chat Backend | Scope §5.3 — Timer visible to both parties.
26 | Audio Call Screen (Frontend) | Call screen: caller/expert avatars, call duration timer, mute/unmute, speaker toggle, end call. Agora RTC SDK (client). | Frontend | Critical | Not Started | Deepak | Sprint 4 (D22–D28) | 19 May 2025 | Agora Backend integration | Scope §5.3 — Per-minute billing runs during call.
27 | Session Start/End Flow & State Machine | Session lifecycle: initiated → active → ended. Practitioner accept/decline. Wallet pre-check before start. Post-session: billing summary, rating prompt. | Backend | Critical | Not Started | Backend Lead | Sprint 4 (D22–D28) | 19 May 2025 | Agora + Chat + Billing Engine | Scope §5.3 — Auto-end on wallet zero + 60s grace.
28 | Text-to-Speech Feature (Accessibility) | TTS integration for chat messages — aids users with reading difficulties. Integrate Azure Cognitive Services Speech or Web Speech API. | Backend | Medium | Not Started | Backend Lead | Sprint 4 (D22–D28) | 19 May 2025 | Chat Infrastructure | Accessibility feature. Azure Cognitive Services Speech SDK.
▸ SPRINT 5 (D29–D35) — Practitioner App & Admin Panel MVP
29 | Practitioner App – Onboarding & KYC Upload | Practitioner registration: personal details, specialties, certifications, bio, languages, per-minute rate. Aadhaar/PAN upload to Azure Blob (private). Pending approval state. | Frontend | Critical | Not Started | Deepak | Sprint 5 (D29–D35) | 26 May 2025 | Azure Blob KYC, Auth APIs | Scope §5.9 — KYC review before practitioner goes live.
30 | Practitioner App – Availability Toggle & Session Handling | Online/Offline/Busy toggle. Incoming session notifications with accept/decline. Active session interface (chat + call controls). Session history view. | Frontend | Critical | Not Started | Deepak | Sprint 5 (D29–D35) | 26 May 2025 | Session State Machine | Scope §5.9 — Real-time availability via Socket.IO.
31 | Practitioner Earnings Dashboard (Frontend) | Daily/weekly/monthly earnings chart. Pending payout balance. Completed session log. Payout request form with bank/UPI details. | Frontend | High | Not Started | Rahul | Sprint 5 (D29–D35) | 26 May 2025 | Per-Minute Billing Engine | Scope §5.9 — Critical for practitioner retention.
32 | Admin Panel – User & Practitioner Management | Web admin: user list (search, suspend, delete), practitioner KYC review queue (approve/reject), set featured practitioners, manage earnings splits. | Frontend | High | Not Started | Rahul | Sprint 5 (D29–D35) | 26 May 2025 | Auth APIs, Profile APIs | Scope §5.10 — Next.js admin panel. shadcn/ui components.
33 | Admin Panel – Session & Dispute Management | View all sessions (active, completed, disputed). Flag sessions for review. Initiate refunds from admin. Real-time active session counter. | Frontend | High | Not Started | Rahul | Sprint 5 (D29–D35) | 26 May 2025 | Session APIs | Scope §5.10 — Payout trigger above threshold needs manual review.
34 | Admin Panel – Payout Processing | Payout request review queue. Approve/reject payouts. Mark as paid. Razorpay payout API integration for bank transfers. | Backend | High | Not Started | Backend Lead | Sprint 5 (D29–D35) | 26 May 2025 | Razorpay Integration, Earnings Dashboard | Scope §5.10 — Manual review for large payouts.
▸ SPRINT 6A (D36–D40) — Ratings, Notifications & Support
35 | Ratings & Reviews System | Post-session 1–5 star rating prompt. Written review submission. Aggregate rating calculation on practitioner profile. Review moderation flag. | Backend | High | Not Started | Backend Lead | Sprint 6A (D36–D40) | 1 Jun 2025 | Session State Machine | Scope §5.3, §5.9 — Review visible on expert profile.
36 | Push Notifications (FCM via Azure Notification Hubs) | Push notification service: new session request, session reminder (24h + 30min before), wallet low balance alert, payout processed. FCM token management. | Backend | High | Not Started | Backend Lead | Sprint 6A (D36–D40) | 1 Jun 2025 | Azure Notification Hubs | Scope §5.5, §7.4 — Single hub for iOS (APNs) + Android (FCM).
37 | Session History & Chat Transcripts | User-facing session history list with past sessions, duration, cost, practitioner. Viewable chat transcript per session. Export as PDF (optional). | Frontend | Medium | Not Started | Deepak | Sprint 6A (D36–D40) | 1 Jun 2025 | Chat Infrastructure | Scope §5.3 — Transcripts stored in PostgreSQL.
38 | In-App Support Chat (Basic) | Simple support ticket/chat widget for users to report issues. Creates a support ticket in the admin panel. Email notification to support team. | Backend | Medium | Not Started | Backend Lead | Sprint 6A (D36–D40) | 1 Jun 2025 | Auth APIs | Scope §5.10 — Support queue in admin panel.
39 | Authentication & Authorization (Role-Based Access Control) | RBAC: roles = user, practitioner, admin. Middleware enforcement on all API routes. Admin-only routes protected. Practitioner routes scoped to their own data. | Backend | Critical | Not Started | Backend Lead | Sprint 6A (D36–D40) | 1 Jun 2025 | JWT Auth, Middleware Protection | Scope §9.2 — OWASP compliant. Must complete before launch.
▸ SPRINT 6B (D41–D43) — Full QA Pass
40 | Functional Testing – Core User Flows | E2E test: register → top-up wallet → find practitioner → start chat session → billing deducted → rate → session history. iOS + Android real devices. | QA | Critical | Not Started | QA Engineer | Sprint 6B (D41–D43) | 4 Jun 2025 | All Sprint 1–6A tasks | Scope §6 Phase 1 — Functional + regression suite.
41 | Payment Flow & Wallet Testing | Razorpay sandbox: all payment methods (UPI, card, net banking). Wallet debit precision. Refund flows. Edge cases: payment timeout, duplicate payment attempt. | QA | Critical | Not Started | QA Engineer | Sprint 6B (D41–D43) | 4 Jun 2025 | Razorpay Integration, Billing Engine | Must test all recharge denominations. PCI-DSS compliance check.
42 | Performance Benchmarking | API p95 response time < 300ms. App cold start < 3s on mid-range Android. Chat latency < 200ms. Load test: 10,000 concurrent users via Azure Load Testing. | QA | High | Not Started | QA Engineer | Sprint 6B (D41–D43) | 4 Jun 2025 | Azure Infra provisioned | Scope §9.1 — Azure Load Testing service.
43 | Security Audit (OWASP Top 10) | OWASP Top 10 review: injection, broken auth, XSS, IDOR, SSRF, misconfiguration. Dependency vulnerability scan (npm audit). TLS 1.3 verification. | QA | Critical | Not Started | QA Engineer | Sprint 6B (D41–D43) | 4 Jun 2025 | All backend tasks | Scope §9.2 — Must resolve all Critical and High findings before launch.
▸ LAUNCH (D44–D45) — Production Go-Live
44 | Simple Deployment – Azure Production Go-Live | Deploy to Azure App Service production slot. Configure custom domain, SSL certificate. DNS propagation. Smoke test on production. | DevOps | Critical | Not Started | DevOps Eng. | Launch (D44–D45) | 6 Jun 2025 | All QA tasks passed | Scope §7.4 — Production multi-AZ. 99.9% uptime SLA.
45 | Docker Setup & Containerisation | Dockerise Node.js backend. Docker Compose for local dev. Azure Container Apps for staging environment. Image registry in Azure Container Registry. | DevOps | High | Not Started | DevOps Eng. | Launch (D44–D45) | 6 Jun 2025 | CI/CD Pipeline | Scope §7.4 — Azure Container Apps for scale-to-zero microservices.
46 | Deployment on Docker (Staging → Production) | Blue-green deployment strategy via Azure deployment slots. Automated health checks. Rollback procedure documented. | DevOps | High | Not Started | DevOps Eng. | Launch (D44–D45) | 6 Jun 2025 | Docker Setup | Zero-downtime deployment via slot swap.
47 | App Store (iOS) & Play Store (Android) Submission | Prepare store listings: screenshots, descriptions, content rating, privacy policy. Submit for review. Apple: spiritual content disclosure. Google: Play policy compliance. | Assets | Critical | Not Started | DevOps Eng. | Launch (D44–D45) | 6 Jun 2025 | All QA tasks passed | Scope §10 — App Store rejection risk. Disclose spiritual content.
48 | Monitoring & Alerting Setup (Azure Monitor + Sentry) | Configure Azure Application Insights dashboards. Sentry error tracking. PagerDuty/email alerts for p0 incidents (downtime, payment failures, high error rates). | DevOps | High | Not Started | DevOps Eng. | Launch (D44–D45) | 6 Jun 2025 | Production deployment | Scope §7.4 — Azure Monitor + App Insights + Sentry.
49 | Adding Tarainfotech Mail for OTP (Email Config) | Configure sending domain tarainfotech.com in SendGrid / Azure Communication Services. SPF, DKIM, DMARC records. Test OTP delivery end-to-end. | Assets | High | Not Started | DevOps Eng. | Launch (D44–D45) | 6 Jun 2025 | Email Verification backend | Domain DNS config required. SendGrid sender verification.
50 | Cost Analysis & Azure Budget Alert Setup | Estimate monthly Azure spend (App Service, PostgreSQL, Redis, Blob, CDN, Notification Hubs). Set budget alerts at 80% and 100% thresholds. Document cost per 1000 sessions. | Assets | Medium | Not Started | DevOps Eng. | Launch (D44–D45) | 6 Jun 2025 | Azure Infra provisioned | Azure Cost Management + Budgets. Track GMV vs. infra spend.
51 | API Documentation & Use-Case Diagram | Swagger/OpenAPI 3.0 docs for all endpoints. Use-case diagram (UML). Postman collection export. Onboarding guide for new developers. | Assets | Medium | Not Started | Backend Lead | Launch (D44–D45) | 6 Jun 2025 | All backend APIs | Scope §12 — API docs deliverable. Host on Azure API Management developer portal.

## 📈 Phase 2 — Growth (D46–90)
HealConnect — Phase 2 — Growth Features ¦ Self-Service Tools, Content Hub, Appointments, Marketplace ¦ D46–D90
Phase 2 — Growth Features ¦ Self-Service Tools, Content Hub, Appointments, Marketplace ¦ D46–D90
# | TASK NAME | DESCRIPTION | TASK TYPE | PRIORITY | STATUS | ASSIGNED TO | SPRINT / WEEK | DUE DATE | DEPENDENCIES | NOTES / RELATED DOCS
▸ WEEK 7–8 (D46–D52) — Free Self-Service Wellness Tools
1 | Numerology Calculator (Backend + Frontend) | Life path, expression, soul urge, and personality numbers from name + DOB. REST API + mobile UI. Share results card. | Backend | High | Not Started | TBD | Week 7–8 (D46–52) | 23 Jun 2025 | Phase 1 complete | Scope §5.6 — SEO-friendly web version too.
2 | Vastu Room Analyser (Backend + Frontend) | Room type + cardinal direction input → Vastu compliance tips and remedies. Pre-defined ruleset. Share/save results. | Backend | High | Not Started | TBD | Week 7–8 (D46–52) | 23 Jun 2025 | Phase 1 complete | Scope §5.6
3 | Chakra Assessment Quiz | 7-question quiz determining energy imbalances. Result: chakra balance report with recommendations. 7 chakra visualisation wheel. | Frontend | Medium | Not Started | TBD | Week 7–8 (D46–52) | 23 Jun 2025 | Phase 1 complete | Scope §5.6
4 | Birth Chart / Kundli Generator | Vedic birth chart from DOB + time + place. Swiss Ephemeris or Astro API integration. Render chart SVG on mobile. Downloadable PDF report. | Backend | High | Not Started | TBD | Week 7–8 (D46–52) | 23 Jun 2025 | Phase 1 complete | Scope §5.6 — Use Swiss Ephemeris library.
5 | Crystal Finder & Daily Affirmation | Crystal-to-intention/zodiac matching engine. Daily affirmation personalised to life path number. Auspicious muhurat suggestions. | Frontend | Low | Not Started | TBD | Week 7–8 (D46–52) | 23 Jun 2025 | Numerology Calculator | Scope §5.6 — Engagement/retention feature.
▸ WEEK 8–9 (D53–D60) — Content Hub & Daily Feed
6 | Blog / Content Hub (Sanity CMS Integration) | Headless CMS (Sanity.io) for articles, guides, meditations. Next.js SSR for SEO. Tag-based filtering. Related articles widget. | Backend | High | Not Started | TBD | Week 8–9 (D53–60) | 30 Jun 2025 | Phase 1 complete | Scope §5.7, §13 — Sanity.io CMS. SEO-optimised.
7 | Daily Personalised Numerology/Healing Feed | Daily feed on home screen: personalised horoscope, numerology forecast, healing tip — based on user's life path number and DOB. | Backend | Medium | Not Started | TBD | Week 8–9 (D53–60) | 30 Jun 2025 | Numerology Calculator, Sanity CMS | Scope §5.7 — Drives DAU retention.
8 | Video Library (Short-form Tips & Guided Meditations) | Video content feed. Thumbnail grid, playback screen. Azure Blob + CDN for video delivery. Bookmark/save videos. | Frontend | Medium | Not Started | TBD | Week 8–9 (D53–60) | 30 Jun 2025 | Azure CDN | Scope §5.7 — Video hosted on Azure Blob + CDN.
▸ WEEK 9–10 (D61–D68) — Scheduled Appointments
9 | Appointment Booking System (Backend) | Practitioner availability calendar API. Slot booking with conflict detection. Rescheduling and cancellation with configurable refund policy. | Backend | High | Not Started | TBD | Week 9–10 (D61–68) | 7 Jul 2025 | Session State Machine | Scope §5.5 — Calendar view + slot availability.
10 | Appointment Booking UI (Frontend) | Calendar date picker. Available time slots. Session type selection (chat/audio). Booking confirmation screen. My Appointments screen. | Frontend | High | Not Started | TBD | Week 9–10 (D61–68) | 7 Jul 2025 | Appointment Backend | Scope §5.5 — Reminder push 24h + 30min before.
▸ WEEK 10–11 (D69–D76) — Live Sessions
11 | Live Session Streaming (Agora Live / Mux) | Practitioner hosts paid/free live streams. User joins and asks questions in real time. Tipping during live session (wallet debit). Stream recording (optional). | Backend | Medium | Not Started | TBD | Week 10–11 (D69–76) | 14 Jul 2025 | Agora Integration, Wallet System | Scope §5.7, §13 — Agora Live or Mux.
12 | Live Session UI (Frontend) | Live session viewer screen: video player, Q&A chat overlay, tip button, viewer count. Host controls: go live, end stream, mute audience. | Frontend | Medium | Not Started | TBD | Week 10–11 (D69–76) | 14 Jul 2025 | Live Session Backend | Scope §5.7
▸ WEEK 11–13 (D77–D90) — Digital Marketplace & Growth Tools
13 | Digital Marketplace – Reports & E-Books | Practitioners list digital products: Vastu reports, numerology reports, natal charts, remedy plans. Purchase via wallet. Instant download post-purchase. | Backend | High | Not Started | TBD | Week 11–13 (D77–90) | 28 Jul 2025 | Wallet System, Azure Blob | Scope §5.8 — Seller dashboard for practitioners.
14 | Coupon Engine & Referral Programme | Admin creates discount codes (% or flat). Referral link generation. Referral credits on successful signup. Coupon validation at wallet recharge. | Backend | Medium | Not Started | TBD | Week 11–13 (D77–90) | 28 Jul 2025 | Wallet System | Scope §5.4, §5.10 — KPI: wallet recharge conversion 20% → 35%.
15 | Dashboard Section Design (Figma Assets) | Design full user and practitioner dashboard screens: home feed, session quick-start, earnings overview, tool shortcuts. Dark + light theme variants. | Assets | High | Not Started | UI/UX Designer | Week 11–13 (D77–90) | 28 Jul 2025 | Phase 1 complete | Design assets for Phase 2 dashboard.
16 | Create Dashboard (Frontend Implementation) | Implement the dashboard home screen per Figma designs. Quick-access cards for tools, recent sessions, feed, practitioner spotlight. | Frontend | High | Not Started | Rahul | Week 11–13 (D77–90) | 28 Jul 2025 | Dashboard Figma Assets | Scope §5 — Central UX hub.
17 | Library Feature (Saved Practitioners, Bookmarked Content) | User library: saved/favourite practitioners, bookmarked articles, saved wellness tools results, purchased digital products. | Frontend | Medium | Not Started | Deepak | Week 11–13 (D77–90) | 28 Jul 2025 | Dashboard, Content Hub | Scope §5.2 — User Management (Library CRUD).
18 | Dark & Light Theme (Session Cookie Toggle) | System-wide dark/light mode toggle. Theme preference stored in session cookies and synced to user profile. Tailwind dark: classes throughout. | Frontend | Low | Not Started | Deepak | Week 11–13 (D77–90) | 28 Jul 2025 | Dashboard | Store in session cookies per original spec.
19 | Fun Facts Loading Screen (Story Theme) | Themed loading screens with rotating wellness/healing facts, affirmations, or practitioner tips. Tied to the story/theme of the app. Enhances perceived performance. | Frontend | Low | Not Started | Deepak | Week 11–13 (D77–90) | 28 Jul 2025 | Dashboard | Engagement/delight feature. Lottie animation preferred.
20 | User Management – Library CRUD Operations (Backend) | APIs for saved practitioners, bookmarked content, reading history. Efficient CRUD with pagination. Sync across devices. | Backend | Medium | Not Started | TBD | Week 11–13 (D77–90) | 28 Jul 2025 | Phase 1 Auth, DB Schema | Scope — Library feature backend.
21 | Account Management (Backend – Profile Edit, Delete, GDPR) | User account edit: name, DOB, profile photo, wellness interests, notification settings. Account deletion with data purge. Password/PIN reset. | Backend | Medium | Not Started | TBD | Week 11–13 (D77–90) | 28 Jul 2025 | Phase 1 Auth | Scope §5.1, §9.4 — GDPR-ready for Phase 2 international.
22 | Account Management (Frontend – Settings Screen) | Settings screen: edit profile, change language, notification prefs, dark/light mode, logout, delete account. Help & support entry. | Frontend | Medium | Not Started | Rahul | Week 11–13 (D77–90) | 28 Jul 2025 | Account Management Backend | Scope §5.1
23 | Getting Temporary Domain & SSL Certificate | Register a temporary domain for staging/beta. Issue Let's Encrypt or Azure-managed SSL cert. Configure HTTPS redirect. Update CORS config. | DevOps | High | Not Started | DevOps Eng. | Week 11–13 (D77–90) | 28 Jul 2025 | Azure App Service | Scope §9.2 — TLS 1.3. Needed for beta user testing.
24 | Push Campaign Tool in Admin Panel | Admin can send targeted push notifications to user segments (all users, active users, wallet-low users, inactive > 7 days). Schedule and track delivery. | Frontend | Medium | Not Started | Rahul | Week 11–13 (D77–90) | 28 Jul 2025 | Azure Notification Hubs, Admin Panel | Scope §5.10 — Segmented push campaigns.

## 🔭 Phase 3 — Scale (D91–160)
HealConnect — Phase 3 — Scale & Monetisation ¦ Physical Marketplace, Video, AI, International Expansion ¦ D91–D160
Phase 3 — Scale & Monetisation ¦ Physical Marketplace, Video, AI, International Expansion ¦ D91–D160
# | TASK NAME | DESCRIPTION | TASK TYPE | PRIORITY | STATUS | ASSIGNED TO | SPRINT / WEEK | DUE DATE | DEPENDENCIES | NOTES / RELATED DOCS
▸ WEEKS 14–16 (D91–D105) — Physical Marketplace
1 | Physical Product Marketplace – Seller Onboarding | Sellers (practitioners) list physical products: crystals, yantras, incense, healing tools. Inventory management, pricing, shipping policy. | Backend | Medium | Not Started | TBD | Week 14–16 (D91–105) | TBD | Digital Marketplace | Scope §5.8
2 | Physical Marketplace – Cart, Checkout & Order Tracking | Add to cart, checkout with address input, Razorpay payment. Order confirmation, fulfilment status, returns flow. | Backend | Medium | Not Started | TBD | Week 14–16 (D91–105) | TBD | Seller Onboarding | Scope §5.8
3 | Puja/Ritual Booking Service | Practitioner offers puja/ritual services. User selects ritual type, date, and receives instructions. Payment via wallet or direct. | Backend | Low | Not Started | TBD | Week 16–17 (D106–115) | TBD | Appointment System | Scope §5.8
▸ WEEKS 17–18 (D116–D125) — Video Call & International Payments
4 | Video Call Integration (Agora RTC – Video) | Enable Agora video channel type. Video call screen with camera toggle, speaker, end call. Per-minute billing same as audio. | Backend | High | Not Started | TBD | Week 17–18 (D116–125) | TBD | Agora Audio Integration | Scope §5.3 — Deferred from Phase 1.
5 | Stripe Integration (International Payments) | Stripe payment gateway for international cards. Multi-currency wallet recharge. GST/VAT compliance for international users. | Backend | High | Not Started | TBD | Week 17–18 (D116–125) | TBD | Wallet System | Scope §5.4, §13 — Phase 2 Stripe integration.
▸ WEEKS 18–20 (D126–D135) — AI Personalisation
6 | AI Personalisation Engine – Practitioner Recommendations | ML-based recommendation engine suggesting practitioners based on: user history, birth chart, wellness goals, session ratings. Collaborative filtering. | Backend | Medium | Not Started | TBD | Week 18–20 (D126–135) | TBD | Session History, Ratings | Scope §6 Phase 3 — AI/ML + Backend.
7 | Community Q&A Module | User-posted wellness questions. Practitioners and community members answer. Upvote system. Moderation queue in admin panel. | Backend | Medium | Not Started | TBD | Week 20–21 (D136–145) | TBD | Phase 2 complete | Scope §5.7
8 | Practitioner Badges & Ranking System | Achievement badges (100 sessions, 4.8+ rating, Top Healer etc.). Ranking on expert discovery page. Badge display on profile. | Backend | Low | Not Started | TBD | Week 20–21 (D136–145) | TBD | Ratings System | Scope §6 Phase 3
▸ WEEKS 21–23 (D146–D160) — Performance, Security & v2 Launch
9 | Performance Optimisation & Load Testing | Optimise DB queries (indexes, query plans). CDN cache tuning. App bundle size reduction. React Native performance profiling. Azure Load Testing to 100K concurrent users. | QA | High | Not Started | TBD | Week 21–23 (D146–160) | TBD | All Phase 3 features | Scope §9.1 — Scale to 100K concurrent.
10 | Full Security Audit & GDPR Compliance | Third-party penetration test. GDPR data rights implementation (export, erasure). PDPB (India) compliance review. Dependency audit. | QA | Critical | Not Started | TBD | Week 21–23 (D146–160) | TBD | All Phase 3 features | Scope §9.2, §9.4 — Required for international launch.
11 | v2.0 Production Launch | Deploy Phase 3 features to production. Update App Store and Play Store listings. Press release / growth marketing campaign. Monitor KPIs vs. Month 6 targets. | DevOps | Critical | Not Started | TBD | Week 21–23 (D146–160) | TBD | Security Audit passed | Scope §11 — Month 6: 25K users, 500 practitioners, ₹20L GMV/month.

## 📊 KPIs & Milestones
HealConnect — KPIs, Milestones & Success Metrics
SUCCESS METRICS (from Scope §11)
Metric | Month 1 Target | Month 6 Target | Owner | Measurement Method | Current | Status
Registered Users | 500 | 25,000 | Growth | Firebase Analytics / DB count | 0 | Not Started
Active Practitioners | 50 | 500 | Ops | Admin panel practitioner count | 0 | Not Started
Sessions Completed / Day | 30 | 500 | Product | Session table daily aggregate | 0 | Not Started
App Store Rating | ≥ 4.2 | ≥ 4.5 | Product | App Store Connect / Play Console | — | Not Started
Wallet Recharge Conversion | 20% | 35% | Growth | (Recharged users / Registered) % | 0% | Not Started
D30 Retention Rate | — | ≥ 25% | Product | Mixpanel retention cohort | — | Not Started
Gross Merchandise Value | ₹50,000 | ₹20,00,000/mo | Finance | Razorpay dashboard + wallet debits | ₹0 | Not Started
API p95 Response Time | < 300ms | < 300ms | DevOps | Azure Application Insights | — | Not Started
App Cold Start (Android) | < 3 sec | < 3 sec | Mobile | Firebase Performance Monitoring | — | Not Started
Chat Message Latency | < 200ms | < 200ms | Backend | Socket.IO ping measurement | — | Not Started
Platform Uptime | 99.9% | 99.9% | DevOps | Azure Monitor uptime check | — | Not Started
PHASE MILESTONES
Milestone | Day | Date (Est.) | Phase | Go/No-Go Criteria | Owner | Status
Design System & Figma Lock | D7 | 28 Apr 2025 | Phase 1 | All screens approved. No redesigns after this. | UI/UX Designer | Not Started
Azure Infrastructure Live | D7 | 28 Apr 2025 | Phase 1 | All Azure services provisioned and reachable. | DevOps Eng. | Not Started
Auth APIs + DB Schema Ready | D14 | 5 May 2025 | Phase 1 | OTP, Google, Apple Sign-in working end-to-end. | Backend Lead | Not Started
Wallet + Razorpay Live (Sandbox) | D21 | 12 May 2025 | Phase 1 | Successful test recharge ₹99 via UPI sandbox. | Backend Lead | Not Started
Real-Time Chat + Audio Call MVP | D28 | 19 May 2025 | Phase 1 | End-to-end session: chat + audio + billing working. | Backend Lead | Not Started
Practitioner App + Admin MVP | D35 | 26 May 2025 | Phase 1 | KYC upload, approve, session accept/decline. | Deepak / Rahul | Not Started
Full QA Pass | D43 | 4 Jun 2025 | Phase 1 | Zero P0 bugs. OWASP audit cleared. | QA Engineer | Not Started
Production Launch (MVP) | D45 | 6 Jun 2025 | Phase 1 | App Store + Play Store live. 50 practitioners onboarded. | All Teams | Not Started
Free Wellness Tools Live | D52 | 23 Jun 2025 | Phase 2 | Numerology, Vastu, Chakra quiz working. | Backend + Mobile | Not Started
Content Hub Live | D60 | 30 Jun 2025 | Phase 2 | Blog with 10+ articles. Daily feed personalised. | Backend + Frontend | Not Started
Appointment Booking Live | D68 | 7 Jul 2025 | Phase 2 | End-to-end booking, reminder notification tested. | Mobile + Backend | Not Started
Digital Marketplace Live | D84 | 21 Jul 2025 | Phase 2 | Practitioners can list + sell digital reports. | Backend + Mobile | Not Started
Phase 2 Complete | D90 | 28 Jul 2025 | Phase 2 | All Phase 2 deliverables shipped. KPIs tracking. | All Teams | Not Started
Video Call + Stripe Live | D125 | TBD | Phase 3 | Video sessions working. Stripe international payment. | Backend + Mobile | Not Started
v2.0 Launch | D160 | TBD | Phase 3 | Physical marketplace, AI, Community Q&A live. | All Teams | Not Started